# PROJECT PLAN

## Kodexo Labs Inbound Sales Qualification Voice Agent

Document ID: KL-PP-VOICE-003 — companion to KL-FSD-VOICE-006 (v6)

Version 1.0 — Draft

# Purpose & How to Read This Plan

This plan defines the build in ordered phases with dependencies and exit criteria — the sequence and gating logic, not calendar dates. The FSD (KL-FSD-VOICE-006) deliberately excludes scheduling and durations from its own scope; this document fills that gap in sequence, but duration estimates depend on team size and availability, which weren't specified. Add estimated durations per phase once capacity is known — flagged again in the closing note below.

Phases are mostly sequential, but several can overlap: Phase 3 (data layer) can run alongside Phase 2 (telephony foundation); Phase 8 (dashboard) can start as soon as the schema in Phase 3 is stable, in parallel with Phases 4–7; Phase 9 (legal/compliance) should be kicked off in Phase 1 so its external lead time doesn't sit on the critical path later.

# Phases

## Phase 1 — Prerequisites & Account Setup

Confirm access to every account/key the build depends on, provision infrastructure, and start the one workstream with an external lead time — legal review.

Key tasks

- Confirm Twilio account access; provision a new Elastic SIP Trunk

- Confirm DeepSeek API key access

- Select and sign up for STT provider (Deepgram recommended) and TTS provider (Cartesia or ElevenLabs recommended)

- Confirm Supabase project access

- Confirm n8n instance access (existing, on VPS)

- Confirm Slack KL-bot channel + webhook access

- Provision a VPS node for self-hosted LiveKit (2–4 vCPU / 4–8GB RAM starting size)

- Kick off legal review of AI-disclosure requirements per jurisdiction (FSD Section 4.5) — start now since it can gate launch

Depends on

Nothing — this is the starting phase.

Exit criteria

All accounts/keys confirmed, LiveKit node provisioned, legal review formally initiated.

## Phase 2 — Telephony & LiveKit Foundation

Get a real phone call reaching a LiveKit room and back out again, before any conversation logic exists.

Key tasks

- Deploy self-hosted LiveKit server (media + SIP) on the provisioned VPS node

- Configure the Twilio Elastic SIP Trunk to route to LiveKit's SIP endpoint

- Verify a test call reaches LiveKit and a room is created

- Deploy a minimal placeholder Agent worker that joins the room and plays a static greeting

Depends on

Phase 1 (Twilio trunk, LiveKit node).

Exit criteria

A real inbound call connects Twilio → LiveKit → worker, and caller hears the placeholder greeting.

## Phase 3 — Data Layer (Supabase Schema)

Stand up the tables every later phase reads from and writes to.

Key tasks

- Create agents, departments, knowledge_base, and call_logs tables per FSD Section 6

- Seed one test agent record with minimal config and one department/transfer-number row

Depends on

Phase 1 (Supabase access). Can run in parallel with Phase 2.

Exit criteria

Schema deployed; one test agent + department row present for use in Phase 4 onward.

## Phase 4 — Agent Worker Core Pipeline

Build the live STT → DeepSeek → TTS loop with native interruption handling — the conversational engine itself.

Key tasks

- Integrate Deepgram STT into the worker

- Integrate direct DeepSeek calls for conversational reasoning (no n8n hop per turn)

- Integrate Cartesia/ElevenLabs TTS into the worker

- Implement native barge-in / interruption handling

- Implement per-call conversation state persistence

Depends on

Phase 2 (LiveKit + worker skeleton), Phase 3 (test agent config to read from).

Exit criteria

Worker holds a basic free-form spoken conversation end to end and stops talking cleanly when interrupted.

## Phase 5 — Call Flow & Business Logic

Implement the actual qualification script: classification, qualifying questions, special cases, and transfer.

Key tasks

- Implement call classification: real project inquiry / wants-a-human / sales pitch / scam (FSD Section 3.3)

- Implement the qualifying sequence: project type → new-or-existing → prior engagement → timeline

- Implement the "wants a human / no AI" special case: one clarifying question, then immediate transfer

- Implement the sales-pitch single decline line, and immediate end for scam/fake-verification calls

- Implement off-topic Q&A answered from the knowledge_base, then return to the flow

- Implement the silent transfer tool call (cold/blind transfer via LiveKit SIP), with the handoff line always spoken first

- Implement the transfer-failure fallback: apologize, explain a callback is coming, capture callback number

Depends on

Phase 4 (working conversational pipeline), Phase 3 (department directory, knowledge base).

Exit criteria

Full scripted flow is testable against every reference scenario in FSD Sections 3.3 and 3.5.

## Phase 6 — n8n Integration — Notifications & Logging

Move Slack notifications and post-call logging out of the worker and into n8n, matching the production message formats.

Key tasks

- Build the n8n workflow for the standard call summary → Slack KL-bot (FSD Section 5.3.1)

- Build the n8n workflow for the urgent @channel transfer-failure alert (FSD Section 5.3.2)

- Build post-call logging to Supabase call_logs (transcript, recording reference, duration, outcome)

Depends on

Phase 5 (transfer success/failure events to trigger on), Phase 3 (call_logs table).

Exit criteria

Both notification types fire correctly and match the production Slack format for every test-call outcome.

## Phase 7 — Human-Likeness Tuning

Turn a functionally-correct agent into one that sounds like a person, per FSD Section 4.

Key tasks

- Configure the pronunciation dictionary, starting with "Kodexo Labs", for both TTS output and STT term boosting

- Tune LLM temperature, max reply length, TTS stability, speech rate, VAD threshold, interruption sensitivity, backchannel frequency (FSD Section 4.3)

- Implement the "Are you AI?" deflection set with rotation so no line repeats across calls

- Listen to a batch of real call recordings and iterate on whichever parameter feels off

Depends on

Phase 5 (full call flow to tune against). Continues in the background through later phases.

Exit criteria

Internal team review confirms the agent reads as human on a sample of real recorded calls.

## Phase 8 — Dashboard

Give admins a no-code way to configure and monitor agents, per FSD Section 5.4.

Key tasks

- Build the agent list view: status, assigned number, last-call timestamp

- Build agent create/edit forms: persona, prompt, qualification criteria, department directory, knowledge base, pronunciation dictionary, humanness parameters, Slack templates

- Build the call log viewer: transcript, recording playback, filters by date/agent/outcome/transfer-failure

- Implement basic role separation between config editors and log viewers

Depends on

Phase 3 (schema) for data model; can start in parallel with Phases 4–7 once schema is stable.

Exit criteria

An admin can create a second agent and edit an existing one's config with no code change or redeploy.

## Phase 9 — Compliance Sign-off

Close out the one workstream that can legally block launch.

Key tasks

- Finalize AI-disclosure requirements per jurisdiction with legal counsel

- Update greeting scripts to fold in required disclosure language naturally, where applicable

Depends on

Phase 1 (review kicked off early so it doesn't sit on the critical path here).

Exit criteria

Legal sign-off obtained for every jurisdiction the live numbers will serve.

## Phase 10 — QA & End-to-End Testing

Verify the whole system against the FSD's functional requirements before it takes a real call.

Key tasks

- Run every branch: real inquiry, wants-a-human, sales pitch, scam, off-topic Q&A, successful transfer, failed transfer

- Load-test a handful of concurrent calls

- Verify Slack notifications and Supabase call_logs are correct for every scenario

- Walk FR-01 through FR-25 and confirm each is demonstrably met

Depends on

Phases 5, 6, 7, 8 all functionally complete.

Exit criteria

All functional requirements pass; no known open defect blocks a real call.

## Phase 11 — Launch & Monitor

Cut the real number over and watch it closely.

Key tasks

- Cut over the live Twilio number to the new pipeline

- Monitor the first batch of real calls closely; retune Section 4.3 parameters as needed

- Confirm auto-restart / reliability behavior for the LiveKit server and agent worker (FSD Section 9)

Depends on

Phase 9 (legal sign-off) and Phase 10 (QA passed) — both are hard gates.

Exit criteria

System is handling real inbound calls in production, with monitoring in place.

# Dependency Overview

| Phase | Depends on | Can overlap with |
| --- | --- | --- |
| 1. Prerequisites & Account Setup | — | — |
| 2. Telephony & LiveKit Foundation | 1 | 3 |
| 3. Data Layer (Supabase Schema) | 1 | 2, 8 (once stable) |
| 4. Agent Worker Core Pipeline | 2, 3 | — |
| 5. Call Flow & Business Logic | 3, 4 | — |
| 6. n8n Integration | 3, 5 | 7, 8 |
| 7. Human-Likeness Tuning | 5 | 6, 8, 10 (ongoing) |
| 8. Dashboard | 3 | 4, 5, 6, 7 |
| 9. Compliance Sign-off | 1 (started early) | 2–8 |
| 10. QA & End-to-End Testing | 5, 6, 7, 8 | — |
| 11. Launch & Monitor | 9, 10 | — |

# Open Item

No calendar durations are assigned above — provide team size/availability and I'll turn this phase sequence into a dated schedule.