# PROJECT PLAN

## Kodexo Labs Inbound Sales Qualification Voice Agent

Document ID: KL-PP-VOICE-003 — companion to KL-FSD-VOICE-006 (v6)

Version 2.0 — Draft (adds dynamic Twilio number management and a tools framework beyond FSD v6's base scope)

# Scope Additions Beyond FSD v6

Two capabilities were agreed after the FSD v6 was written and are reflected in this plan's phases below, but are not yet written into the FSD itself:

1. Dynamic Twilio number management

Rather than a single hardcoded number, the dashboard manages numbers directly through Twilio's API: searching available numbers, purchasing one for a new agent, and attaching/releasing it against one shared SIP trunk (the trunk itself is created once and stays static — only the numbers attached to it change). Routing which agent owns a given call is a Supabase lookup on the dialed number, not a Twilio-side per-number configuration — this is what makes "add agent #2" a pure dashboard action with no telephony reconfiguration.

2. Open tools framework (Vapi-style function calling)

The FSD names exactly two tools (call-tracking, transfer) but explicitly allows for "any future tools" (FR-08a). This plan generalizes that into an open framework: a new tools table (agent_id, name, description, parameter_schema, webhook_url) lets an admin define a custom tool from the dashboard and assign it to any agent. Built-in tools (transfer, call-tracking) remain code inside the agent worker; custom business tools (calendar booking, CRM lookups, order status, etc.) run by calling the tool's configured n8n webhook, so new integrations are a dashboard action and an n8n workflow, not new worker code. All tool invocations remain silent per FR-08a, regardless of tier.

Recommendation: fold both of these into a future FSD revision (v7) so the requirements document and the build stay in sync — flagging it here in the meantime so the plan doesn't silently drift from the spec.

# Purpose & How to Read This Plan

This plan defines the build in ordered phases with dependencies and exit criteria — the sequence and gating logic, not calendar dates. The FSD (KL-FSD-VOICE-006) deliberately excludes scheduling and durations from its own scope; this document fills that gap in sequence, but duration estimates depend on team size and availability, which weren't specified. Add estimated durations per phase once capacity is known — flagged again in the closing note below.

Phases are mostly sequential, but several can overlap: Phase 3 (data layer) can run alongside Phase 2 (telephony foundation); Phase 8 (dashboard) can start as soon as the schema in Phase 3 is stable, in parallel with Phases 4–7; Phase 9 (legal/compliance) should be kicked off in Phase 1 so its external lead time doesn't sit on the critical path later.

# Phases

## Phase 1 — Prerequisites & Account Setup

Confirm access to every account/key the build depends on, provision infrastructure, and start the one workstream with an external lead time — legal review.

Key tasks

- Confirm Twilio account access; provision a new Elastic SIP Trunk

- Confirm DeepSeek API key access

- Select and sign up for STT provider (Deepgram recommended) and TTS provider (Cartesia or ElevenLabs recommended)

- Confirm Supabase project access

- Confirm n8n instance access (existing, on VPS)

- Confirm Slack KL-bot channel + webhook access

- Provision a VPS node for self-hosted LiveKit (2–4 vCPU / 4–8GB RAM starting size)

- Kick off legal review of AI-disclosure requirements per jurisdiction (FSD Section 4.5) — start now since it can gate launch

Depends on

Nothing — this is the starting phase.

Exit criteria

All accounts/keys confirmed, LiveKit node provisioned, legal review formally initiated.

## Phase 2 — Telephony & LiveKit Foundation

Get a real phone call reaching a LiveKit room and back out again, before any conversation logic exists.

Key tasks

- Deploy self-hosted LiveKit server (media + SIP) on the provisioned VPS node

- Configure the Twilio Elastic SIP Trunk to route to LiveKit's SIP endpoint

- Verify a test call reaches LiveKit and a room is created

- Deploy a minimal placeholder Agent worker that joins the room and plays a static greeting

Depends on

Phase 1 (Twilio trunk, LiveKit node).

Exit criteria

A real inbound call connects Twilio → LiveKit → worker, and caller hears the placeholder greeting.

## Phase 3 — Data Layer (Supabase Schema)

Stand up the tables every later phase reads from and writes to.

Key tasks

- Create agents, departments, knowledge_base, and call_logs tables per FSD Section 6

- Create a tools table (tool_id, agent_id FK, name, description, parameter_schema, webhook_url) — the dashboard-configurable tools framework added in v2 of this plan (see Scope Additions)

- Seed one test agent record with minimal config and one department/transfer-number row

Depends on

Phase 1 (Supabase access). Can run in parallel with Phase 2.

Exit criteria

Schema deployed; one test agent + department row present for use in Phase 4 onward.

## Phase 4 — Agent Worker Core Pipeline

Build the live STT → DeepSeek → TTS loop with native interruption handling — the conversational engine itself.

Key tasks

- Integrate Deepgram STT into the worker

- Integrate direct DeepSeek calls for conversational reasoning (no n8n hop per turn)

- Integrate Cartesia/ElevenLabs TTS into the worker

- Implement native barge-in / interruption handling

- Implement per-call conversation state persistence

Depends on

Phase 2 (LiveKit + worker skeleton), Phase 3 (test agent config to read from).

Exit criteria

Worker holds a basic free-form spoken conversation end to end and stops talking cleanly when interrupted.

## Phase 5 — Call Flow & Business Logic

Implement the actual qualification script: classification, qualifying questions, special cases, and transfer.

Key tasks

- Implement call classification: real project inquiry / wants-a-human / sales pitch / scam (FSD Section 3.3)

- Implement the qualifying sequence: project type → new-or-existing → prior engagement → timeline

- Implement the "wants a human / no AI" special case: one clarifying question, then immediate transfer

- Implement the sales-pitch single decline line, and immediate end for scam/fake-verification calls

- Implement off-topic Q&A answered from the knowledge_base, then return to the flow

- Implement the silent transfer tool call (cold/blind transfer via LiveKit SIP), with the handoff line always spoken first

- Implement the transfer-failure fallback: apologize, explain a callback is coming, capture callback number

- Build the generic tool-calling framework: load the list of tools attached to the current agent_id, register them with DeepSeek's function-calling interface, execute the call, and feed the result back into the conversation — all silently (FR-08a)

- Built-in tools (transfer, call-tracking) stay as code inside the worker; custom/business tools (calendar booking, CRM lookup, order status, etc.) execute by calling the tool's configured n8n webhook, so new integrations don't require new worker code

Depends on

Phase 4 (working conversational pipeline), Phase 3 (department directory, knowledge base, tools table).

Exit criteria

Full scripted flow is testable against every reference scenario in FSD Sections 3.3 and 3.5, and a sample custom tool (via n8n webhook) can be invoked silently mid-call.

## Phase 6 — n8n Integration — Notifications & Logging

Move Slack notifications and post-call logging out of the worker and into n8n, matching the production message formats.

Key tasks

- Build the n8n workflow for the standard call summary → Slack KL-bot (FSD Section 5.3.1)

- Build the n8n workflow for the urgent @channel transfer-failure alert (FSD Section 5.3.2)

- Build post-call logging to Supabase call_logs (transcript, recording reference, duration, outcome)

Depends on

Phase 5 (transfer success/failure events to trigger on), Phase 3 (call_logs table).

Exit criteria

Both notification types fire correctly and match the production Slack format for every test-call outcome.

## Phase 7 — Human-Likeness Tuning

Turn a functionally-correct agent into one that sounds like a person, per FSD Section 4.

Key tasks

- Configure the pronunciation dictionary, starting with "Kodexo Labs", for both TTS output and STT term boosting

- Tune LLM temperature, max reply length, TTS stability, speech rate, VAD threshold, interruption sensitivity, backchannel frequency (FSD Section 4.3)

- Implement the "Are you AI?" deflection set with rotation so no line repeats across calls

- Listen to a batch of real call recordings and iterate on whichever parameter feels off

Depends on

Phase 5 (full call flow to tune against). Continues in the background through later phases.

Exit criteria

Internal team review confirms the agent reads as human on a sample of real recorded calls.

## Phase 8 — Dashboard

Give admins a no-code way to configure and monitor agents, per FSD Section 5.4.

Key tasks

- Build the agent list view: status, assigned number, last-call timestamp

- Build agent create/edit forms: persona, prompt, qualification criteria, department directory, knowledge base, pronunciation dictionary, humanness parameters, Slack templates

- Build the tools management UI: create a tool (name, description, parameters, webhook URL) and attach/detach it to any agent — no code change (Scope Addition, see below)

- Build the Twilio number management UI: search available numbers, purchase, and attach/release against the shared SIP trunk, per agent

- Build the call log viewer: transcript, recording playback, filters by date/agent/outcome/transfer-failure

- Implement basic role separation between config editors and log viewers

Depends on

Phase 3 (schema) for data model; can start in parallel with Phases 4–7 once schema is stable.

Exit criteria

An admin can create a second agent and edit an existing one's config with no code change or redeploy.

## Phase 9 — Compliance Sign-off

Close out the one workstream that can legally block launch.

Key tasks

- Finalize AI-disclosure requirements per jurisdiction with legal counsel

- Update greeting scripts to fold in required disclosure language naturally, where applicable

Depends on

Phase 1 (review kicked off early so it doesn't sit on the critical path here).

Exit criteria

Legal sign-off obtained for every jurisdiction the live numbers will serve.

## Phase 10 — QA & End-to-End Testing

Verify the whole system against the FSD's functional requirements before it takes a real call.

Key tasks

- Run every branch: real inquiry, wants-a-human, sales pitch, scam, off-topic Q&A, successful transfer, failed transfer

- Load-test a handful of concurrent calls

- Verify Slack notifications and Supabase call_logs are correct for every scenario

- Walk FR-01 through FR-25 and confirm each is demonstrably met

Depends on

Phases 5, 6, 7, 8 all functionally complete.

Exit criteria

All functional requirements pass; no known open defect blocks a real call.

## Phase 11 — Launch & Monitor

Cut the real number over and watch it closely.

Key tasks

- Cut over the live Twilio number to the new pipeline

- Monitor the first batch of real calls closely; retune Section 4.3 parameters as needed

- Confirm auto-restart / reliability behavior for the LiveKit server and agent worker (FSD Section 9)

Depends on

Phase 9 (legal sign-off) and Phase 10 (QA passed) — both are hard gates.

Exit criteria

System is handling real inbound calls in production, with monitoring in place.

# Dependency Overview

| Phase | Depends on | Can overlap with |
| --- | --- | --- |
| 1. Prerequisites & Account Setup | — | — |
| 2. Telephony & LiveKit Foundation | 1 | 3 |
| 3. Data Layer (Supabase Schema) | 1 | 2, 8 (once stable) |
| 4. Agent Worker Core Pipeline | 2, 3 | — |
| 5. Call Flow & Business Logic | 3, 4 | — |
| 6. n8n Integration | 3, 5 | 7, 8 |
| 7. Human-Likeness Tuning | 5 | 6, 8, 10 (ongoing) |
| 8. Dashboard | 3 | 4, 5, 6, 7 |
| 9. Compliance Sign-off | 1 (started early) | 2–8 |
| 10. QA & End-to-End Testing | 5, 6, 7, 8 | — |
| 11. Launch & Monitor | 9, 10 | — |

# Open Item

No calendar durations are assigned above — provide team size/availability and I'll turn this phase sequence into a dated schedule.